## Project plan
| Select scenario: | Plan |  | Current Date | 2021-07-13
Total Milestone days of work
Individual activity days of work planned
Activity days completed
Project Planned Days
| Data Input for chart |  | Plan |  |  | Actual |  |  | Data prep:
|  |  | #working |  |  | #working |  | % | Project Timeline: Plan v/s Actual |  | Actual |  |  | Plan
Task # | Task | Start date | Individual activity days of work | End date | Start date | Activity days completed | End date | Completion | Task index | Start date | Activity days completed | # days completed | Plan Start date | Project Planned Days | Y Axis for plan | Today arrow indicator | Holiday Calendar
1 | Project Preparation | 2021-04-12 | 5 | 2021-04-19 | 2021-04-12 | 7 | 2021-04-21 | 83.33% | Project Preparation (5 WD) + 2 | 2021-04-12 | 9 | 7.5 | 2021-04-12 | 7 | 38.9 |  | 2021-04-02
2 | Project Charter | 2021-04-12 | 1 | 2021-04-13 | 2021-04-12 | 3 | 2021-04-15 | 100% | Project Charter (1 WD) + 2 | 2021-04-12 | 3 | 3 | 2021-04-12 | 1 | 37.8 |  | 2021-05-02
3 | Project contract & financial terms sign off | 2021-04-13 | 3 | 2021-04-16 | 2021-04-15 | 3 | 2021-04-20 | 100% | Project contract & financial terms sign off (3 WD) + 0 | 2021-04-15 | 5 | 5 | 2021-04-13 | 3 | 36.6
4 | Resource Allocation | 2021-04-16 | 1 | 2021-04-19 | 2021-04-20 | 1 | 2021-04-21 | 50% | Resource Allocation (1 WD) + 0 | 2021-04-20 | 1 | 0.5 | 2021-04-16 | 3 | 35.5 | 2021-04-19
5 | Business Requirement, Business Process & IT Assesement | 2021-04-19 | 13 | 2021-05-06 | 2021-04-21 | 13 | 2021-05-10 |  | Business Requirement, Business Process & IT Assesement (13 WD) + 0 | 2021-04-21 | 19 | 0 | 2021-04-19 | 17 | 34.3 | 2021-04-19
6 | Proposed project statement of work & schedule | 2021-04-19 | 1 | 2021-04-20 | 2021-04-19 | 1 | 2021-04-20 |  | Proposed project statement of work & schedule (1 WD) + 0 | 2021-04-19 | 1 | 0 | 2021-04-19 | 1 | 33 | 2021-04-19
7 | Define roles and responsibilites | 2021-04-19 | 1 | 2021-04-20 | 2021-04-19 | 1 | 2021-04-20 |  | Define roles and responsibilites (1 WD) + 0 | 2021-04-19 | 1 | 0 | 2021-04-19 | 1 | 31.9 | 2021-04-19
8 | Map business Process KPI | 2021-04-20 | 5 | 2021-04-27 | 2021-04-20 | 5 | 2021-04-27 |  | Map business Process KPI (5 WD) + 0 | 2021-04-20 | 7 | 0 | 2021-04-20 | 7 | 31 | 2021-04-19
9 | Employee survey | 2021-04-20 | 5 | 2021-04-27 | 2021-04-20 | 5 | 2021-04-27 |  | Employee survey (5 WD) + 0 | 2021-04-20 | 7 | 0 | 2021-04-20 | 7 | 29.6 | 2021-04-19
10 | Gather requirements from stakeholders | 2021-04-20 | 5 | 2021-04-27 | 2021-04-20 | 5 | 2021-04-27 |  | Gather requirements from stakeholders (5 WD) + 0 | 2021-04-20 | 7 | 0 | 2021-04-20 | 7 | 28.5 | 2021-04-19
11 | Establish performance baseline for ROI | 2021-04-27 | 2 | 2021-04-29 | 2021-04-27 | 2 | 2021-04-29 |  | Establish performance baseline for ROI (2 WD) + 0 | 2021-04-27 | 2 | 0 | 2021-04-27 | 2 | 27.3 | 2021-04-19
12 | Conduct Risk/Technical Assesement | 2021-04-29 | 5 | 2021-05-06 | 2021-04-29 | 5 | 2021-05-06 |  | Conduct Risk/Technical Assesement (5 WD) + 0 | 2021-04-29 | 7 | 0 | 2021-04-29 | 7 | 26.2 | 2021-04-19
13 | Platform configuration | 2021-05-06 | 12 | 2021-05-24 | 2021-05-06 | 12 | 2021-05-24 |  | Platform configuration (12 WD) + 0 | 2021-05-06 | 18 | 0 | 2021-05-06 | 18 | 25.2 | 2021-04-19
14 | Platform configuration for user role | 2021-05-06 | 1 | 2021-05-07 | 2021-05-06 | 1 | 2021-05-07 |  | Platform configuration for user role (1 WD) + 0 | 2021-05-06 | 1 | 0 | 2021-05-06 | 1 | 24 | 2021-04-19
15 | Data exchange handshake configuration | 2021-05-07 | 3 | 2021-05-12 | 2021-05-07 | 3 | 2021-05-12 |  | Data exchange handshake configuration (3 WD) + 0 | 2021-05-07 | 5 | 0 | 2021-05-07 | 5 | 22.5 | 2021-04-19
16 | Platform customization requirements | 2021-05-12 | 5 | 2021-05-19 | 2021-05-12 | 5 | 2021-05-19 |  | Platform customization requirements (5 WD) + 0 | 2021-05-12 | 7 | 0 | 2021-05-12 | 7 | 21.5 | 2021-04-19
17 | Single sign on data configuration | 2021-05-19 | 3 | 2021-05-24 | 2021-05-19 | 3 | 2021-05-24 |  | Single sign on data configuration (3 WD) + 0 | 2021-05-19 | 5 | 0 | 2021-05-19 | 5 | 20.5 | 2021-04-19
18 | Implementation plan | 2021-05-24 | 11 | 2021-06-08 | 2021-05-24 | 11 | 2021-06-08 |  | Implementation plan (11 WD) + 0 | 2021-05-24 | 15 | 0 | 2021-05-24 | 15 | 19.5 | 2021-04-19
19 | Product demo with client team/UAT | 2021-05-24 | 1 | 2021-05-25 | 2021-05-24 | 1 | 2021-05-25 |  | Product demo with client team/UAT (1 WD) + 0 | 2021-05-24 | 1 | 0 | 2021-05-24 | 1 | 18.2 | 2021-04-19
20 | Deploy training manual | 2021-05-25 | 3 | 2021-05-28 | 2021-05-25 | 3 | 2021-05-28 |  | Deploy training manual (3 WD) + 0 | 2021-05-25 | 3 | 0 | 2021-05-25 | 3 | 17.2 | 2021-04-19
21 | LMS content mapping sign off | 2021-05-28 | 2 | 2021-06-01 | 2021-05-28 | 2 | 2021-06-01 |  | LMS content mapping sign off (2 WD) + 0 | 2021-05-28 | 4 | 0 | 2021-05-28 | 4 | 15.8 | 2021-04-19
22 | Setup customer support channels | 2021-06-01 | 1 | 2021-06-02 | 2021-06-01 | 1 | 2021-06-02 |  | Setup customer support channels (1 WD) + 0 | 2021-06-01 | 1 | 0 | 2021-06-01 | 1 | 14.8 | 2021-04-19
23 | Plan communication and stakeholder engagement | 2021-06-02 | 2 | 2021-06-04 | 2021-06-02 | 2 | 2021-06-04 |  | Plan communication and stakeholder engagement (2 WD) + 0 | 2021-06-02 | 2 | 0 | 2021-06-02 | 2 | 13.7 | 2021-04-19
24 | Perform risk identification, analysis and response planning | 2021-06-04 | 1 | 2021-06-07 | 2021-06-04 | 1 | 2021-06-07 |  | Perform risk identification, analysis and response planning (1 WD) + 0 | 2021-06-04 | 3 | 0 | 2021-06-04 | 3 | 12.4 | 2021-04-19
25 | Formal Approval | 2021-06-07 | 1 | 2021-06-08 | 2021-06-07 | 1 | 2021-06-08 |  | Formal Approval (1 WD) + 0 | 2021-06-07 | 1 | 0 | 2021-06-07 | 1 | 11.4 | 2021-04-19
26 | Engagement Plan | 2021-06-08 | 5 | 2021-06-15 | 2021-06-08 | 5 | 2021-06-15 |  | Engagement Plan (5 WD) + 0 | 2021-06-08 | 7 | 0 | 2021-06-08 | 7 | 10.2 | 2021-04-19
27 | Marketing collateral delivery schedule for product go live | 2021-06-08 | 1 | 2021-06-09 | 2021-06-08 | 1 | 2021-06-09 |  | Marketing collateral delivery schedule for product go live (1 WD) + 0 | 2021-06-08 | 1 | 0 | 2021-06-08 | 1 | 9 | 2021-04-19
28 | Train the trainer programs; training schedule & logistics | 2021-06-09 | 4 | 2021-06-15 | 2021-06-09 | 4 | 2021-06-15 |  | Train the trainer programs; training schedule & logistics (4 WD) + 0 | 2021-06-09 | 6 | 0 | 2021-06-09 | 6 | 7.9 | 2021-04-19
29 | Go Live | 2021-06-15 | 10 | 2021-06-29 | 2021-06-15 | 10 | 2021-06-29 |  | Go Live (10 WD) + 0 | 2021-06-15 | 14 | 0 | 2021-06-15 | 14 | 6.7 | 2021-04-19
30 | Training & comm. For onboarding users | 2021-06-15 | 1 | 2021-06-16 | 2021-06-15 | 1 | 2021-06-16 |  | Training & comm. For onboarding users (1 WD) + 0 | 2021-06-15 | 1 | 0 | 2021-06-15 | 1 | 5.7 | 2021-04-19
31 | Rollout program analytics and report project performance | 2021-06-16 | 9 | 2021-06-29 | 2021-06-16 | 9 | 2021-06-29 |  | Rollout program analytics and report project performance (9 WD) + 0 | 2021-06-16 | 13 | 0 | 2021-06-16 | 13 | 4.6 | 2021-04-19
32 | Post go live support and lessons learnt | 2021-06-29 | 5 | 2021-07-06 | 2021-06-29 | 5 | 2021-07-06 |  | Post go live support and lessons learnt (5 WD) + 0 | 2021-06-29 | 7 | 0 | 2021-06-29 | 7 | 3.3 | 2021-04-19
33 | Support client queries through established channels | 2021-06-29 | 5 | 2021-07-06 | 2021-06-29 | 5 | 2021-07-06 |  | Support client queries through established channels (5 WD) + 0 | 2021-06-29 | 7 | 0 | 2021-06-29 | 7 | 2.3 | 2021-04-19
34 | New feature delivery & regression testing | 2021-06-29 | 5 | 2021-07-06 | 2021-06-29 | 5 | 2021-07-06 |  | New feature delivery & regression testing (5 WD) + 0 | 2021-06-29 | 7 | 0 | 2021-06-29 | 7 | 1.3 | 2021-04-19
35 | Index & archive records, complete financial closure and gain final acceptance | 2021-06-29 | 5 | 2021-07-06 | 2021-06-29 | 5 | 2021-07-06 |  | Index & archive records, complete financial closure and gain final acceptance (5 WD) + 0 | 2021-06-29 | 7 | 0 | 2021-06-29 | 7 | 0.3 | 2021-04-19
Formulas:
End date = (IF([Start date]="","",(WORKDAY([Start date],[Plan],U43:U53))))
End date = (IF([Start date]="","",(WORKDAY([Start date],[Actual],U43:U53))))
Start date = [Start date]
Start date = [End date, row above]
Plan Start date = [Start date]